## Sheet1
Task Id | Task Name | Start Date | Finish Date | Duration | Predecessors | Resource
1 | Batelco Bahrain CMP deployment | Wed 05-02-25 | Tue 17-11-26 | 434 days
1.1 | Project Initiation | Wed 05-02-25 | Thu 27-02-25 | 17 days
1.1.1 | PO sign off | Wed 05-02-25 | Wed 05-02-25 | 1 day |  | Batelco
1.1.2 | Kick Off meeting | Wed 26-02-25 | Thu 27-02-25 | 2 days | 1.1.1[FS+1 wk] | Airlinq,Batelco,Thales
1.2 | Design | Sun 09-03-25 | Sun 25-05-25 | 50 days
1.2.1 | Requirement gathering | Sun 09-03-25 | Sun 18-05-25 | 45 days
1.2.1.1 | Business requirements Design | Sun 09-03-25 | Sun 04-05-25 | 35 days
1.2.1.1.1 | CMP walkthrough | Sun 09-03-25 | Mon 10-03-25 | 2 days | 1.1.2[FS+1 wk] | Thales,Airlinq
1.2.1.1.2 | CMP business flows | Tue 11-03-25 | Thu 13-03-25 | 3 days | 1.2.1.1.1 | Thales,Airlinq
1.2.1.1.3 | Customer Onboarding Design | Sun 16-03-25 | Sun 04-05-25 | 6 days | 1.2.1.1.2 | Batelco,Thales,Airlinq
1.2.1.1.4 | SIM Ordering Process | Sun 16-03-25 | Sun 04-05-25 | 6 days | 1.2.1.1.2 | Batelco,Thales,Airlinq
1.2.1.1.5 | Provisioning process Flow | Sun 16-03-25 | Sun 04-05-25 | 6 days | 1.2.1.1.2 | Batelco,Thales,Airlinq
1.2.1.1.6 | Billing and Invoice Process | Sun 16-03-25 | Sun 04-05-25 | 6 days | 1.2.1.1.2 | Batelco,Thales,Airlinq
1.2.1.1.7 | Online Charging flow | Sun 16-03-25 | Sun 04-05-25 | 6 days | 1.2.1.1.2 | Batelco,Thales,Airlinq
1.2.1.2 | Business Requirement Design review & update | Mon 12-05-25 | Thu 15-05-25 | 4 days | 1.2.1.1 | Airlinq,Batelco,Thales
1.2.1.3 | Business Requirement Design (BRD) sign off | Sun 18-05-25 | Sun 18-05-25 | 1 day | 1.2.1.2 | Batelco
1.2.1.4 | Customer Requirement Specs Sign-off | Sun 18-05-25 | Sun 18-05-25 | 0 days | 1.2.1.3
1.2.2 | High level Design | Mon 05-05-25 | Sun 25-05-25 | 15 days
1.2.2.1 | High level solution architecture preparation and submission | Mon 05-05-25 | Wed 14-05-25 | 8 days | 1.2.1.1 | Thales,Airlinq
1.2.2.2 | HLD review and workshop | Thu 15-05-25 | Mon 19-05-25 | 3 days | 1.2.2.1 | Batelco,Airlinq,Thales
1.2.2.3 | HLD update (if needed) | Tue 20-05-25 | Wed 21-05-25 | 2 days | 1.2.2.2 | Thales,Airlinq
1.2.2.4 | HLD final review | Thu 22-05-25 | Sun 25-05-25 | 2 days | 1.2.2.3 | Batelco,Airlinq,Thales
1.2.2.5 | High Level Design Closure | Sun 25-05-25 | Sun 25-05-25 | 0 days | 1.2.2.4
1.3 | Cloud Readiness | Sun 02-03-25 | Sun 29-03-26 | 257 days
1.3.1 | Cloud Design Readiness (Cloud LLD) | Sun 02-03-25 | Sun 11-05-25 | 45 days
1.3.1.1 | Initial HLD finalized including cloud(BOM Finalization) | Sun 02-03-25 | Thu 13-03-25 | 10 days | 1.1.2
1.3.1.2 | Submit & Finalize detailed infrastructure requirements (e.g. VLANs, Traffic types and flow, bandwidth, etc.) | Sun 16-03-25 | Wed 16-04-25 | 20 days | 1.3.1.1 | Thales,Airlinq,Batelco
1.3.1.3 | Submit & Finalize IP and VLAN requirements for VMs | Thu 17-04-25 | Sun 11-05-25 | 15 days | 1.3.1.2 | Thales,Airlinq,Batelco
1.3.1.4 | Submit & Finalize IP requirements for CMP and TAC (public and private, VLANs, etc.) | Thu 17-04-25 | Sun 11-05-25 | 15 days | 1.3.1.2 | Thales,Airlinq,Batelco
1.3.1.5 | Network Protocol finalization | Thu 17-04-25 | Sun 11-05-25 | 15 days | 1.3.1.2 | Batelco
1.3.1.6 | Share bandwidth requirements | Sun 16-03-25 | Wed 16-04-25 | 20 days | 1.1.2,1.3.1.1 | Thales,Airlinq
1.3.1.7 | DNS finalization | Thu 17-04-25 | Thu 24-04-25 | 5 days | 1.3.1.2 | Batelco
1.3.1.8 | NTP finalization | Thu 17-04-25 | Thu 24-04-25 | 5 days | 1.3.1.2 | Batelco
1.3.1.9 | WAF | Thu 17-04-25 | Thu 08-05-25 | 14 days | 1.3.1.2 | Batelco,Thales
1.3.1.10 | Hostnames finalization | Mon 05-05-25 | Sun 11-05-25 | 5 days | 1.3.1.2[FS+10 days] | Batelco
1.3.2 | Load Balancer Design Readiness | Sun 16-03-25 | Wed 17-09-25 | 120 days |  | Batelco,Airlinq,Thales
1.3.2.1 | Submit and Finalize Load Balancer requirements | Sun 16-03-25 | Tue 08-04-25 | 15 days | 1.1.2,1.3.1.1 | Batelco,Airlinq,Thales
1.3.2.2 | Prepare RFP/RFQ | Wed 09-04-25 | Wed 16-04-25 | 5 days | 1.3.2.1 | Batelco
1.3.2.3 | Evaluation and selection | Thu 17-04-25 | Sun 18-05-25 | 20 days | 1.3.2.2 | Batelco
1.3.2.4 | Ordering and delivery | Mon 19-05-25 | Tue 19-08-25 | 3 mons | 1.3.2.3 | Batelco
1.3.2.5 | Load Balancer design | Wed 20-08-25 | Wed 17-09-25 | 20 days | 1.3.2.4 | Batelco,Airlinq,Thales
1.3.3 | Pre Prod Cloud Readiness | Mon 12-05-25 | Tue 08-07-25 | 35 days
1.3.3.1 | VM Onboarding for Pre Prod | Mon 12-05-25 | Sun 25-05-25 | 2 days | 1.3.1 | Batelco
1.3.3.2 | Network Configuration for Pre Prod VMs | Mon 26-05-25 | Thu 19-06-25 | 3 days | 1.3.3.1 | Batelco
1.3.3.3 | Intra Node network reachability of Pre Prod VMS | Mon 26-05-25 | Thu 19-06-25 | 3 days | 1.3.3.1 | Batelco
1.3.3.4 | Vulnerability scan and hardening | Sun 22-06-25 | Tue 08-07-25 | 2 days | 1.3.3.3
1.3.4 | Prod Cloud Readiness | Tue 13-01-26 | Sun 29-03-26 | 50 days
1.3.4.1 | VM Onboarding for Prod | Tue 13-01-26 | Tue 27-01-26 | 2 days | 1.3.3.3,1.3.2[FS+77 days] | Batelco
1.3.4.2 | Network Configuration for Prod VMs | Wed 28-01-26 | Tue 17-02-26 | 3 days | 1.3.4.1 | Batelco
1.3.4.3 | Intra Node network reachability of Prod VMS | Wed 18-02-26 | Tue 10-03-26 | 3 days | 1.3.4.2 | Batelco
1.3.4.4 | Vulnerability scan and hardening | Wed 11-03-26 | Sun 29-03-26 | 2 days | 1.3.4.3
1.3.5 | VPN Access | Mon 02-06-25 | Tue 17-03-26 | 192 days
1.3.5.1 | Fill VPN requirements sheet | Mon 02-06-25 | Thu 12-06-25 | 5 days | 1.3.3.2[FS-2 days] | Thales,Airlinq
1.3.5.2 | Create supplier staff accounts | Sun 15-06-25 | Thu 19-06-25 | 5 days | 1.3.5.1 | Batelco
1.3.5.3 | Provision Access in LDAP | Sun 22-06-25 | Mon 23-06-25 | 2 days | 1.3.5.2 | Batelco
1.3.5.4 | Provision CSOC access | Tue 24-06-25 | Wed 25-06-25 | 2 days | 1.3.5.3 | Batelco
1.3.5.5 | Provision MobileData firewall | Thu 26-06-25 | Thu 03-07-25 | 5 days | 1.3.5.4 | Batelco
1.3.5.6 | VPN Access Provisioned | Thu 03-07-25 | Thu 03-07-25 | 0 days | 1.3.5.5
1.3.5.7 | Send emails to supplier resources | Tue 08-07-25 | Tue 08-07-25 | 1 day | 1.3.5.6 | Batelco
1.3.5.8 | Test Remote access for Pre Prod VM | Tue 08-07-25 | Mon 14-07-25 | 1 wk | 1.3.5.6,1.3.3.3 | Thales,Airlinq
1.3.5.9 | Test Remote access for Prod VM | Wed 11-03-26 | Tue 17-03-26 | 1 wk | 1.3.4.3,1.3.5.6 | Thales,Airlinq
1.3.6 | Load Balancer Implementation | Thu 18-09-25 | Sun 16-11-25 | 2 mons | 1.3.2.5,1.3.2.4 | Batelco
1.4 | CMP Platform Deployment- Software Delivery | Mon 05-05-25 | Mon 27-04-26 | 237 days
1.4.1 | Pre Prod Base Version Deployment (Vanilla) | Tue 15-07-25 | Wed 20-08-25 | 27 days
1.4.1.1 | Deployment of CMP nodes | Tue 15-07-25 | Mon 04-08-25 | 3 days | 1.3.5.8,1.3.3 | Airlinq,Thales
1.4.1.2 | Deployment Sanity | Tue 05-08-25 | Wed 20-08-25 | 12 days | 1.4.1.1 | Airlinq,Thales
1.4.1.3 | CMP Vanilla deployment | Wed 20-08-25 | Wed 20-08-25 | 0 days | 1.4.1.2
1.4.2 | Prod Base Version Deploy (Vanilla) | Mon 30-03-26 | Mon 27-04-26 | 20 days
1.4.2.1 | Deployment of CMP nodes | Mon 30-03-26 | Mon 20-04-26 | 3 days | 1.4.1,1.3.4,1.3.5.9,1.3.6,1.4.3.6 | Airlinq,Thales
1.4.2.2 | Deployment sanity | Tue 21-04-26 | Mon 27-04-26 | 1 wk | 1.4.2.1 | Airlinq,Thales
1.4.2.3 | Production Readiness | Mon 27-04-26 | Mon 27-04-26 | 0 days | 1.4.2.2
1.4.3 | Pre-Production deployment of Host Network (CMP Provider) | Mon 05-05-25 | Wed 24-09-25 | 95 days
1.4.3.1 | IT Applications Integration Design (LLD) | Mon 05-05-25 | Tue 15-07-25 | 45 days
1.4.3.1.1 | API design for IT interfaces | Mon 05-05-25 | Sun 01-06-25 | 4 days | 1.2.1.1 | Batelco,Thales,Airlinq
1.4.3.1.2 | Revenue Assurance (RA) for Host | Mon 02-06-25 | Tue 08-07-25 | 4 days | 1.4.3.1.1,1.2.2.5[FF] | Airlinq,Batelco,Thales
1.4.3.1.3 | Billing and Rating for Host | Mon 02-06-25 | Tue 08-07-25 | 4 days | 1.4.3.1.1,1.2.2.5[FF] | Airlinq,Batelco,Thales
1.4.3.1.4 | API specs as per customization requirements | Wed 09-07-25 | Tue 15-07-25 | 1 wk | 1.4.3.1.2,1.4.3.1.3
1.4.3.2 | Pre Prod Integrations for Batelco | Wed 16-07-25 | Tue 05-08-25 | 15 days
1.4.3.2.1 | RA and other IT system integrations for Host | Wed 16-07-25 | Tue 05-08-25 | 3 days | 1.4.3.1,1.2.2
1.4.3.3 | custom developments | Wed 16-07-25 | Wed 10-09-25 | 40 days
1.4.3.3.1 | customization for IT interfaces by CMP | Wed 16-07-25 | Wed 10-09-25 | 8 days | 1.4.3.1.4 | Airlinq,Batelco,Thales
1.4.3.3.2 | Billing and Invoice customizations | Wed 16-07-25 | Wed 10-09-25 | 8 days | 1.4.3.1.4 | Airlinq,Batelco,Thales
1.4.3.4 | Use Cases Prepration and Simulators deployment | Thu 21-08-25 | Wed 03-09-25 | 2 days | 1.4.1 | Airlinq,Thales
1.4.3.5 | CMP Host Version Acceptance | Thu 11-09-25 | Wed 24-09-25 | 2 days | 1.4.3.4,1.4.3.3 | Airlinq,Thales
1.4.3.6 | Pre-production Setup Completion (with Host Integration) | Wed 24-09-25 | Wed 24-09-25 | 0 days | 1.4.3.5
1.4.3.7
1.5 | MNO1 Onboarding | Sun 25-05-25 | Tue 17-11-26 | 362 days
1.5.1 | MNO 1 identified and contracted | Sun 25-05-25 | Thu 17-07-25 | 32 days | 1.2.2
1.5.2 | Integration and Testing - Pre Prod | Sun 20-07-25 | Mon 27-04-26 | 190 days
1.5.2.1 | Integration requirements | Sun 20-07-25 | Tue 26-08-25 | 28 days
1.5.2.1.1 | Integration Touchpoints finalization | Sun 20-07-25 | Thu 31-07-25 | 10 days | 1.2.2,1.3.1,1.5.1 | Thales,Batelco,Airlinq
1.5.2.1.2 | Submit questionnaire for Batelco to fill | Sun 03-08-25 | Tue 05-08-25 | 3 days | 1.5.2.1.1 | Thales,Airlinq
1.5.2.1.3 | Fill the requested information | Wed 06-08-25 | Tue 19-08-25 | 10 days | 1.5.2.1.2 | Batelco
1.5.2.1.4 | Joint workshop to review the inputs | Wed 20-08-25 | Tue 26-08-25 | 5 days | 1.5.2.1.3 | Thales,Batelco,Airlinq
1.5.2.1.5 | Interface/Protocol finalization | Sun 03-08-25 | Tue 05-08-25 | 3 days | 1.5.2.1.1 | Thales,Batelco,Airlinq
1.5.2.1.6 | Integration Requirements Closure | Tue 05-08-25 | Tue 05-08-25 | 0 days | 1.5.2.1.5
1.5.2.2 | PreProd and Prod Low Level Design (LLD) | Wed 27-08-25 | Tue 18-11-25 | 57 days
1.5.2.2.1 | IT Applications Integration Design | Wed 27-08-25 | Sun 26-10-25 | 40 days
1.5.2.2.1.1 | Provisioning system design | Wed 27-08-25 | Sun 26-10-25 | 8 days | 1.2.2.5,1.5.2.1 | Airlinq,Batelco,Thales
1.5.2.2.1.2 | IT application integration design (including SSL inputs) | Wed 27-08-25 | Sun 26-10-25 | 8 days | 1.2.2.5,1.5.2.1 | Airlinq,Batelco,Thales
1.5.2.2.1.3 | Sim Vendor / Supply chain | Wed 27-08-25 | Sun 26-10-25 | 8 days | 1.2.2.5,1.5.2.1 | Airlinq,Batelco,Thales
1.5.2.2.1.4 | MSISDN & IMSI ranges finalization | Wed 27-08-25 | Sun 26-10-25 | 8 days | 1.2.2.5,1.5.2.1 | Airlinq,Batelco,Thales
1.5.2.2.1.5 | eUICC Subscription Management | Wed 27-08-25 | Sun 26-10-25 | 8 days | 1.2.2.5,1.5.2.1 | Airlinq,Batelco,Thales
1.5.2.2.1.6 | CRM | Wed 27-08-25 | Sun 26-10-25 | 8 days | 1.2.2.5,1.5.2.1 | Airlinq,Batelco,Thales
1.5.2.2.1.7 | SMTP | Wed 27-08-25 | Sun 26-10-25 | 8 days | 1.2.2.5,1.5.2.1 | Airlinq,Batelco,Thales
1.5.2.2.1.8 | Revenue Assurance (RA) | Wed 27-08-25 | Sun 26-10-25 | 8 days | 1.2.2.5,1.5.2.1 | Airlinq,Batelco,Thales
1.5.2.2.1.9 | Billing and Rating | Wed 27-08-25 | Sun 26-10-25 | 8 days | 1.2.2.5,1.5.2.1 | Airlinq,Batelco,Thales
1.5.2.2.1.10 | Ticketing | Wed 27-08-25 | Sun 26-10-25 | 8 days | 1.2.2.5,1.5.2.1 | Airlinq,Batelco,Thales
1.5.2.2.2 | Core Network design | Wed 27-08-25 | Sun 26-10-25 | 40 days
1.5.2.2.2.1 | Provisioning GW | Wed 27-08-25 | Sun 26-10-25 | 8 days | 1.2.2.5,1.5.2.1 | Airlinq,Batelco,Thales
1.5.2.2.2.2 | PGW/GGSN (for Data Charging) | Wed 27-08-25 | Sun 26-10-25 | 8 days | 1.2.2.5,1.5.2.1 | Airlinq,Batelco,Thales
1.5.2.2.2.3 | IMS/MSC | Wed 27-08-25 | Sun 26-10-25 | 8 days | 1.2.2.5,1.5.2.1 | Airlinq,Batelco,Thales
1.5.2.2.2.4 | MSC / STP / SMSC | Wed 27-08-25 | Sun 26-10-25 | 8 days | 1.2.2.5,1.5.2.1 | Airlinq,Batelco,Thales
1.5.2.2.2.5 | Monitoring Application | Wed 27-08-25 | Sun 26-10-25 | 8 days | 1.2.2.5,1.5.2.1 | Airlinq,Batelco,Thales
1.5.2.2.2.6 | Voice Camel Design | Wed 27-08-25 | Sun 26-10-25 | 8 days | 1.2.2.5,1.5.2.1 | Airlinq,Batelco,Thales
1.5.2.2.2.7 | SMSC Design | Wed 27-08-25 | Sun 26-10-25 | 8 days | 1.2.2.5,1.5.2.1 | Airlinq,Batelco,Thales
1.5.2.2.2.8 | Billing / EMM Integration design | Wed 27-08-25 | Sun 26-10-25 | 8 days | 1.2.2.5,1.5.2.1 | Airlinq,Batelco,Thales
1.5.2.2.3 | LLD Finalization and Approval | Mon 03-11-25 | Tue 18-11-25 | 12 days
1.5.2.2.3.1 | LLD submission | Mon 03-11-25 | Mon 03-11-25 | 1 day | 1.5.2.2.2,1.5.2.2.1[FS+5 days] | Thales,Airlinq
1.5.2.2.3.2 | LLD review and workshop | Tue 04-11-25 | Thu 06-11-25 | 3 days | 1.5.2.2.3.1 | Batelco,Thales,Airlinq
1.5.2.2.3.3 | LLD update (if needed) | Sun 09-11-25 | Thu 13-11-25 | 5 days | 1.5.2.2.3.2 | Thales,Airlinq
1.5.2.2.3.4 | LLD final review | Sun 16-11-25 | Tue 18-11-25 | 3 days | 1.5.2.2.3.3 | Batelco
1.5.2.2.3.5 | Low Level Design Closure | Tue 18-11-25 | Tue 18-11-25 | 0 days | 1.5.2.2.3.4
1.5.2.3 | Integration | Wed 19-11-25 | Tue 03-03-26 | 70 days
1.5.2.3.1 | Integration Checklist Completion | Wed 19-11-25 | Thu 18-12-25 | 20 days | 1.5.2.2
1.5.2.3.1.1 | IT nodes communication matrix | Wed 19-11-25 | Thu 18-12-25 | 4 days |  | Airlinq,Thales,Batelco
1.5.2.3.1.2 | Network Nodes communication matrix | Wed 19-11-25 | Thu 18-12-25 | 4 days |  | Airlinq,Thales,Batelco
1.5.2.3.1.3 | Folder structure for EMM | Wed 19-11-25 | Thu 18-12-25 | 4 days |  | Airlinq,Batelco,Thales
1.5.2.3.1.4 | Core Network Integration details | Wed 19-11-25 | Thu 18-12-25 | 4 days |  | Airlinq,Batelco,Thales
1.5.2.3.1.5 | API integration details | Wed 19-11-25 | Thu 18-12-25 | 4 days |  | Airlinq,Batelco,Thales
1.5.2.3.1.6 | Finalize SSL Certificates Requirements | Wed 19-11-25 | Tue 02-12-25 | 2 days
1.5.2.3.2 | Network route configuration on Cloud for Pre prod and Prod | Sun 21-12-25 | Sun 28-12-25 | 1 wk | 1.5.2.3.1 | Batelco
1.5.2.3.3 | SSL certificate creation for Pre prod and Prod | Wed 03-12-25 | Mon 05-01-26 | 1 mon | 1.5.2.3.1.6 | Airlinq,Batelco,Thales
1.5.2.3.4 | Firewall configurations for Pre prod and Prod | Sun 21-12-25 | Mon 05-01-26 | 2 days | 1.5.2.3.1 | Batelco
1.5.2.3.5 | M2M IMSI/MSISDN Series Allocation | Sun 21-12-25 | Sun 28-12-25 | 1 wk | 1.5.2.3.1 | Batelco
1.5.2.3.6 | Load Balancer Readiness | Sun 21-12-25 | Sun 28-12-25 | 5 days | 1.3.6,1.5.2.3.1 | Batelco
1.5.2.3.7 | DRA/Sigrtan Integration | Tue 06-01-26 | Mon 19-01-26 | 10 days | 1.5.2.2.2,1.4.1
1.5.2.3.7.1 | DRA/Sigtran network reachability | Tue 06-01-26 | Mon 19-01-26 | 10 days | 1.5.2.3.4,1.4.3 | Airlinq,Batelco,Thales
1.5.2.3.7.1.1 | DRA/Sigtran Configuration | Tue 06-01-26 | Mon 19-01-26 | 2 days |  | Airlinq,Batelco,Thales
1.5.2.3.8 | SMSC Integration | Sun 21-12-25 | Tue 27-01-26 | 25 days
1.5.2.3.8.1 | SMSC Short code assignment | Sun 21-12-25 | Sun 28-12-25 | 1 wk | 1.5.2.3.1 | Batelco
1.5.2.3.8.2 | SMSC reachability | Tue 06-01-26 | Mon 12-01-26 | 1 wk | 1.5.2.3.4,1.4.1 | Airlinq,Batelco,Thales
1.5.2.3.8.3 | SMSC account configuration | Tue 13-01-26 | Tue 27-01-26 | 2 days | 1.5.2.3.8.2,1.5.2.3.8.1 | Airlinq,Batelco,Thales
1.5.2.3.9 | EMM Integration | Sun 21-12-25 | Tue 27-01-26 | 25 days | 1.4.3
1.5.2.3.9.1 | Network reachability with mediation | Sun 21-12-25 | Sun 28-12-25 | 1 wk | 1.5.2.3.1 | Airlinq,Batelco,Thales
1.5.2.3.9.2 | Creation of shared folder | Mon 29-12-25 | Mon 12-01-26 | 2 days | 1.5.2.3.9.1 | Airlinq,Batelco,Thales
1.5.2.3.9.3 | Shared folder SFTP access | Tue 13-01-26 | Tue 27-01-26 | 2 days | 1.5.2.3.9.2 | Airlinq,Batelco,Thales
1.5.2.3.10 | IT and Billing Applications Integration | Sun 21-12-25 | Tue 03-03-26 | 50 days
1.5.2.3.10.1 | APIs Customizations Handshake | Sun 21-12-25 | Tue 03-02-26 | 6 days | 1.5.2.3.1.5 | Airlinq,Batelco,Thales
1.5.2.3.10.2 | Network reachability with IT applications | Wed 04-02-26 | Tue 10-02-26 | 1 wk | 1.5.2.3.10.1 | Airlinq,Batelco,Thales
1.5.2.3.10.3 | TAC integration with CMP | Wed 11-02-26 | Tue 03-03-26 | 3 days | 1.5.2.3.10.2 | Airlinq,Batelco,Thales
1.5.2.3.10.4 | Security Certificate installation | Wed 11-02-26 | Tue 03-03-26 | 3 days | 1.5.2.3.10.2 | Airlinq,Batelco,Thales
1.5.2.3.11 | Security Tools Integration | Sun 21-12-25 | Thu 15-01-26 | 18 days | 1.4.3
1.5.2.3.11.1 | Network reachability with Security tools | Sun 21-12-25 | Sun 28-12-25 | 1 wk | 1.5.2.3.1 | Airlinq,Batelco,Thales
1.5.2.3.11.2 | User creation for security tools | Mon 29-12-25 | Wed 31-12-25 | 3 days | 1.5.2.3.11.1 | Airlinq,Batelco,Thales
1.5.2.3.11.3 | Security Audit | Sun 04-01-26 | Thu 15-01-26 | 2 days | 1.5.2.3.11.2 | Batelco
1.5.2.4 | Custom Development (If Any) | Wed 19-11-25 | Tue 03-03-26 | 70 days | 1.5.2.2
1.5.2.4.1 | Customization for IT interfaces by CMP (If Any) | Wed 19-11-25 | Tue 03-03-26 | 14 days | 1.5.2.2.1 | Airlinq,Batelco,Thales
1.5.2.4.2 | Billing and Invoice customizations (If Any) | Wed 19-11-25 | Tue 03-03-26 | 14 days | 1.5.2.2.1 | Airlinq,Batelco,Thales
1.5.2.4.3 | Provisioning flow customizations (If Any) | Wed 19-11-25 | Tue 03-03-26 | 14 days | 1.5.2.2.1 | Airlinq,Batelco,Thales
1.5.2.4.4 | API Custom Dev Activities (MNO 1) | Wed 19-11-25 | Mon 19-01-26 | 8 days | 1.5.2.2.1 | Batelco
1.5.2.5 | Testing and Validation | Wed 19-11-25 | Mon 27-04-26 | 105 days
1.5.2.5.1 | System Integration Testing Data Prepration | Wed 04-03-26 | Tue 17-03-26 | 2 days | 1.5.2.3[FS-1 wk] | Batelco
1.5.2.5.2 | System Integration Testing Test Document Creation | Wed 19-11-25 | Thu 18-12-25 | 4 days | 1.5.2.3[SS] | Airlinq,Batelco,Thales
1.5.2.5.3 | System Integration Testing Document Review | Sun 21-12-25 | Mon 12-01-26 | 3 days | 1.5.2.5.2 | Batelco,Thales
1.5.2.5.4 | System Integration Testing Test Document Approval | Tue 13-01-26 | Thu 15-01-26 | 3 days | 1.5.2.5.3 | Batelco
1.5.2.5.5 | System Integration Test Cases Execution | Wed 18-03-26 | Mon 20-04-26 | 4 days | 1.5.2.3,1.5.2.5.1,1.5.2.5.4 | Airlinq,Batelco,Thales
1.5.2.5.6 | End to end Test Cases Execution | Mon 30-03-26 | Mon 27-04-26 | 4 days | 1.5.2.5.5[SS+1 wk] | Airlinq,Batelco,Thales
1.5.2.5.7 | Load Balancer UAT Testing | Mon 30-03-26 | Mon 06-04-26 | 5 days | 1.3.6,1.5.2.5.6[SS] | Batelco
1.5.2.5.8 | WAF Readiness | Mon 30-03-26 | Mon 06-04-26 | 5 days | 1.5.2.5.6[SS] | Batelco
1.5.2.5.9 | Security Assessment (Pre Prod) | Wed 04-03-26 | Mon 06-04-26 | 20 days
1.5.2.5.9.1 | Update security policies and patches | Wed 04-03-26 | Tue 17-03-26 | 2 days | 1.5.2.3 | Airlinq,Batelco,Thales
1.5.2.5.9.2 | Security Audit | Wed 18-03-26 | Mon 06-04-26 | 2 days | 1.5.2.5.9.1 | Batelco
1.5.3 | Training | Wed 04-03-26 | Mon 04-05-26 | 40 days
1.5.3.1 | Training Content Preparation | Wed 04-03-26 | Mon 06-04-26 | 4 days | 1.5.3.2[FF-4 days] | Thales,Airlinq
1.5.3.2 | Training Sessions Delivery | Tue 28-04-26 | Mon 04-05-26 | 1 wk | 1.5.2.5 | Airlinq,Thales,Batelco
1.5.4 | UAT | Wed 11-03-26 | Tue 30-06-26 | 70 days
1.5.4.1 | UAT Pre-requisites | Tue 07-04-26 | Mon 20-04-26 | 10 days
1.5.4.1.1 | Testing SIM Cards Preparations | Tue 07-04-26 | Mon 20-04-26 | 2 days | 1.5.2.3,1.5.4.3[SS-4 days] | Batelco
1.5.4.1.2 | Testing Tariff Plans Preparations | Tue 07-04-26 | Mon 20-04-26 | 2 days | 1.5.2.3,1.5.4.3[SS-4 days] | Batelco
1.5.4.1.3 | Testing Customer Accounts Details | Tue 07-04-26 | Mon 20-04-26 | 2 days | 1.5.2.3,1.5.4.3[SS-4 days] | Batelco
1.5.4.2 | Use Cases Prepration (Subset of Test Cases) | Wed 11-03-26 | Mon 27-04-26 | 6 days | 1.5.2.5.4,1.5.4.3[SS-7 days] | Batelco,Thales,Airlinq
1.5.4.3 | UAT Execution | Tue 05-05-26 | Sun 21-06-26 | 6 days | 1.5.3,1.5.2.5,1.5.2.5.6 | Airlinq,Batelco,Thales
1.5.4.4 | UAT Blocker Issues Resolution | Sun 07-06-26 | Sun 21-06-26 | 2 days | 1.5.4.3[FS-2 days] | Airlinq,Thales
1.5.4.5 | Provisional Acceptance Certificate (PAC) | Tue 30-06-26 | Tue 30-06-26 | 0 days | 1.5.4.4[FS+5 days]
1.5.5 | Production Readiness | Tue 28-04-26 | Tue 04-08-26 | 65 days
1.5.5.1 | Production Customization Deployment (If Any) | Mon 22-06-26 | Tue 07-07-26 | 2 days | 1.5.4.4 | Airlinq,Thales
1.5.5.2 | Integration Prod | Tue 28-04-26 | Tue 04-08-26 | 65 days
1.5.5.2.1 | DRA/Sigtran Integration | Tue 28-04-26 | Mon 18-05-26 | 15 days
1.5.5.2.1.1 | DRA/Sigtran network reachability | Tue 28-04-26 | Mon 11-05-26 | 2 days | 1.5.2.3.4,1.4.2,1.5.2.5 | Airlinq,Batelco,Thales
1.5.5.2.1.2 | DRA/Sigtran configuration | Tue 12-05-26 | Mon 18-05-26 | 1 wk | 1.5.5.2.1.1 | Airlinq,Batelco,Thales
1.5.5.2.2 | SMSC Integration | Tue 28-04-26 | Mon 18-05-26 | 15 days
1.5.5.2.2.1 | SMSC/SMTP reachability | Tue 28-04-26 | Mon 11-05-26 | 2 days | 1.5.2.3.4,1.4.2,1.5.2.5 | Airlinq,Batelco,Thales
1.5.5.2.2.2 | SMSC/SMTP Account configuration | Tue 12-05-26 | Mon 18-05-26 | 1 wk | 1.5.5.2.2.1 | Airlinq,Batelco,Thales
1.5.5.2.3 | EMM/Billing Integration | Tue 28-04-26 | Sun 17-05-26 | 14 days
1.5.5.2.3.1 | Mediation network reachability | Tue 28-04-26 | Mon 11-05-26 | 2 days | 1.5.2.3.4,1.4.2,1.5.2.5 | Airlinq,Batelco,Thales
1.5.5.2.3.2 | SFTP folder creation | Tue 12-05-26 | Wed 13-05-26 | 2 days | 1.5.5.2.3.1 | Airlinq,Batelco,Thales
1.5.5.2.3.3 | SFTP user access | Thu 14-05-26 | Sun 17-05-26 | 2 days | 1.5.5.2.3.2 | Airlinq,Batelco,Thales
1.5.5.2.4 | IT Application Integration | Tue 28-04-26 | Mon 18-05-26 | 15 days
1.5.5.2.4.1 | Network reachability with IT nodes | Tue 28-04-26 | Mon 11-05-26 | 2 days | 1.5.2.3.4,1.4.2,1.5.2.5 | Airlinq,Batelco,Thales
1.5.5.2.4.2 | TAC integration with CMP | Tue 28-04-26 | Mon 11-05-26 | 2 days | 1.5.2.3.4,1.4.2,1.5.2.5
1.5.5.2.4.3 | Security certificate installation | Tue 12-05-26 | Mon 18-05-26 | 1 wk | 1.5.5.2.4.1 | Airlinq,Batelco,Thales
1.5.5.2.5 | Security Tools Integration | Tue 28-04-26 | Mon 18-05-26 | 15 days
1.5.5.2.5.1 | Network reachability for Security tools | Tue 28-04-26 | Mon 11-05-26 | 2 days | 1.5.2.3.4,1.4.2,1.5.2.5 | Airlinq,Batelco,Thales
1.5.5.2.5.2 | User name configurations for Security tools | Tue 12-05-26 | Mon 18-05-26 | 1 wk | 1.5.5.2.5.1 | Airlinq
1.5.5.2.6 | Security Assessment (Prod) | Wed 08-07-26 | Tue 21-07-26 | 2 days | 1.5.5.1,1.5.5.2.5.2 | Batelco,Airlinq,Thales
1.5.5.2.7 | Business Testing | Wed 22-07-26 | Tue 04-08-26 | 2 days | 1.5.5.2.6 | Batelco
1.5.6 | Operational Readiness | Tue 28-04-26 | Tue 25-08-26 | 80 days
1.5.6.1 | LLD Approval (Final LLD submit and approval for handover) | Wed 22-07-26 | Tue 28-07-26 | 1 wk | 1.5.5.2.6 | Airlinq,Batelco,Thales
1.5.6.2 | Monitoring Tool Integration on Prod | Tue 28-04-26 | Mon 11-05-26 | 2 days | 1.5.2.3.4,1.4.2,1.5.2.5 | Airlinq,Batelco,Thales
1.5.6.3 | Operational Tools Integration on Prod | Tue 28-04-26 | Mon 11-05-26 | 2 days | 1.5.2.3.4,1.4.2,1.5.2.5 | Airlinq,Batelco,Thales
1.5.6.4 | ATP (Ops Team Acceptance Testing) | Wed 05-08-26 | Tue 25-08-26 | 3 days | 1.5.6.3,1.5.5.2.7,1.5.6.2 | Batelco,Ailinq,Thales
1.5.7 | Launch Prep / Ready for Service | Wed 26-08-26 | Tue 17-11-26 | 60 days
1.5.7.1 | Smoke Testing | Wed 26-08-26 | Tue 08-09-26 | 2 days | 1.5.6.4 | Batelco,Airlinq,Thales
1.5.7.2 | Final Acceptance Testing (FAC) | Tue 17-11-26 | Tue 17-11-26 | 0 days | 1.5.7.1[FS+5 days],1.5.6.4[FS+3 mons]
1.5.7.3
4 | Batelco Bahrain TAC Deployment | Sun 02-03-25 | Thu 29-10-26 | 404 days
4.1 | Project Kickoff - TAC | Sun 02-03-25 | Mon 03-03-25 | 2 days | 1.1.2 | Batelco,Thales
4.2 | Project Documentation - TAC | Wed 02-04-25 | Sun 01-06-25 | 40 days |  | Batelco,Thales
4.2.1 | System Segment Specification Preparation & Submission | Wed 02-04-25 | Tue 08-04-25 | 5 days | 4.1,1.2.1.1.3[FS-20 days] | Thales
1.6.2.2 | SSS Discussion | Wed 09-04-25 | Sun 04-05-25 | 15 days | 4.2.1 | Batelco,Thales
1.6.2.3 | SSS Approval | Mon 05-05-25 | Sun 11-05-25 | 5 days | 1.6.2.2 | Batelco
4.2.2 | ATP Document Submission | Mon 12-05-25 | Sun 18-05-25 | 5 days | 1.6.2.3 | Thales
1.6.2.5 | ATP Review & Approval | Mon 19-05-25 | Sun 01-06-25 | 10 days | 4.2.2 | Batelco
4.4 | eSIM Profile Development & Pre-requisites | Mon 12-05-25 | Sun 28-09-25 | 92 days
4.4.1 | Prerequisites - Profile Configuration confirmation | Mon 12-05-25 | Tue 15-07-25 | 40 days
4.4.1.1 | IF/OF format confirmation - Confirmation for the current K4 - OP - TK Keys | Mon 12-05-25 | Sun 01-06-25 | 15 days | 1.6.2.3 | Batelco
4.4.1.2 | eSIM Profile identifier - Confirmation for the reference eSIM Profile | Mon 12-05-25 | Sun 01-06-25 | 15 days | 1.6.2.3 | Batelco
4.4.1.3 | Confirmation for PGP keys, Allynis account | Mon 12-05-25 | Sun 01-06-25 | 15 days | 1.6.2.3 | Batelco
4.4.1.4 | IF with 10 subscriptions - test cards | Mon 12-05-25 | Sun 25-05-25 | 10 days | 1.6.2.3 | Batelco
4.4.1.5 | If required Step2 Multipass? (Then we need the above requirements for Step2) | Mon 12-05-25 | Sun 25-05-25 | 10 days | 1.6.2.3 | Batelco
4.4.1.6 | TAC TSD SCP80 / SCP81 / DNS Configuration | Mon 26-05-25 | Thu 19-06-25 | 15 days | 4.4.1.5 | Thales
4.4.1.7 | TAC Applet Configuration requirements | Sun 22-06-25 | Tue 15-07-25 | 15 days | 4.4.1.6 | Batelco
4.4.2 | eUICC card/profile preparation | Wed 16-07-25 | Sun 28-09-25 | 52 days
4.4.2.1 | Electrical Profile Creation on the selected Product (Chip) | Wed 16-07-25 | Sun 20-07-25 | 3 days | 4.4.1.7 | Thales
4.4.2.2 | TAC Applet Configuration implementation | Mon 21-07-25 | Tue 22-07-25 | 2 days | 4.4.2.1 | Thales
4.4.2.3 | EP final implementation | Wed 23-07-25 | Thu 24-07-25 | 2 days | 4.4.2.2 | Thales
4.4.2.4 | Card validation - TAC Applet offline test, Profile Checking, Authentication, OTA .. Etc. | Sun 27-07-25 | Thu 31-07-25 | 5 days | 4.4.2.3 | Thales
4.4.2.5 | DP implementation | Sun 03-08-25 | Wed 06-08-25 | 4 days | 4.4.2.4 | Thales
4.4.2.6 | CPC development | Thu 07-08-25 | Sun 17-08-25 | 7 days | 4.4.2.5 | Thales
4.4.2.7 | Test Data generation - validation | Mon 18-08-25 | Tue 19-08-25 | 2 days | 4.4.2.6 | Thales
4.4.2.8 | Live OF / TAC SCP80 Provisioning file generation | Wed 20-08-25 | Tue 26-08-25 | 5 days | 4.4.2.7 | Thales
1.6.3.2.9 | Preparation of Network settings for IOT/TAC SIM cards | Wed 27-08-25 | Wed 10-09-25 | 10 days | 4.4.2.8 | Batelco
4.4.2.9 | Provisioning of Live OF/ TAC SCP80 file | Thu 11-09-25 | Wed 17-09-25 | 5 days | 1.6.3.2.9 | Batelco,Thales
4.4.2.10 | E2E testing for SIM Profile | Thu 18-09-25 | Sun 28-09-25 | 7 days | 4.4.2.9 | Batelco,Thales
1.6.4 | TAC Installation & Config | Mon 29-09-25 | Wed 19-11-25 | 36 days
1.6.4.1 | Information related to Key Labels - to be received from Thales Technical Consultant | Mon 29-09-25 | Wed 01-10-25 | 3 days | 4.4.2.10 | Thales
1.6.4.2 | Prepare KPF document for KMT | Thu 02-10-25 | Sun 05-10-25 | 2 days | 1.6.4.1 | Thales
1.6.4.3 | Request Key artifacts to KMT | Mon 06-10-25 | Tue 28-10-25 | 15 days | 1.6.4.2 | Thales
1.6.4.4 | Deploy Production TAC tenant on Cloud | Wed 29-10-25 | Tue 04-11-25 | 5 days | 1.6.4.3 | Thales
1.6.4.5 | TAC server configuration | Wed 05-11-25 | Tue 11-11-25 | 5 days | 1.6.4.4 | Thales
1.6.4.6 | Provision cards in TAC server | Wed 12-11-25 | Sun 16-11-25 | 3 days | 1.6.4.5 | Thales
1.6.4.7 | Connectivity Parameter discussion with Thales TC | Mon 17-11-25 | Wed 19-11-25 | 3 days | 1.6.4.6 | Thales
4.5 | Integration& end to end test (TAC only w/o CMP) | Thu 20-11-25 | Tue 20-01-26 | 40 days |  | Batelco,Thales
4.5.1 | Integration between card and TACserver (for polling) | Thu 20-11-25 | Wed 03-12-25 | 10 days | 1.6.4.7 | Thales
4.5.2 | Integration between TAC server and DEMO CMP/fleet manager | Thu 04-12-25 | Wed 10-12-25 | 5 days | 4.5.1 | Thales
4.5.3 | Integration between card and tac server (for indirect download) | Thu 11-12-25 | Sun 21-12-25 | 5 days | 4.5.2 | Thales
4.5.4 | Integration between TAC and SMDP (for indirect download) | Mon 22-12-25 | Mon 29-12-25 | 5 days | 4.5.3 | Thales
4.6 | Pre-ATP | Tue 30-12-25 | Tue 06-01-26 | 5 days | 4.5.4 | Thales
4.7 | ATP Execution as per ATP Document (TAC only) - PHASE1 | Wed 07-01-26 | Tue 20-01-26 | 10 days | 4.6 | Batelco,Thales
1.6.6 | Integration& end to end test (TAC with CMP-PREPROD) | Wed 21-01-26 | Mon 20-04-26 | 59 days
1.6.6.1 | Certificate Signing Request generation | Wed 21-01-26 | Wed 28-01-26 | 5 days | 4.7 | Thales
1.6.6.2 | CSR signing by CMP backend server CA | Thu 29-01-26 | Wed 04-02-26 | 5 days | 1.6.6.1 | Airlinq,Batelco
1.6.6.3 | Integration between TAC server and CMP-PREPROD | Wed 04-03-26 | Tue 10-03-26 | 5 days | 1.5.2.3.10.3,1.6.6.2 | Airlinq,Batelco,Thales
1.6.6.4 | Integration between card and tac server (for indirect download) | Wed 11-03-26 | Tue 17-03-26 | 5 days | 1.6.6.3 | Thales
1.6.6.5 | Integration between TAC and Thales SMDP (for indirect download) | Wed 18-03-26 | Thu 26-03-26 | 4 days | 1.6.6.4 | Thales
1.6.6.6 | Pre-ATP Preprod | Sun 29-03-26 | Mon 06-04-26 | 6 days | 1.6.6.5 | Thales
1.6.6.7 | ATP Execution as per ATP Document with CMP pre prod | Tue 07-04-26 | Mon 20-04-26 | 10 days | 1.6.6.6 | Airlinq,Batelco,Thales
1.6.7 | Integration End to End TAC with CMP-PROD | Tue 21-04-26 | Tue 21-07-26 | 60 days
1.6.7.1 | Certificate Signing Request generation | Tue 21-04-26 | Wed 22-04-26 | 2 days | 1.6.6.7 | Thales
1.6.7.2 | CSR signing by CMP backend server CA | Thu 23-04-26 | Thu 30-04-26 | 6 days | 1.6.7.1 | Airlinq,Batelco
1.6.7.3 | Integration between TAC server and CMP-PROD | Tue 12-05-26 | Mon 25-05-26 | 10 days | 1.6.7.2,1.5.5.2.4.2 | Airlinq,Batelco,Thales
1.6.7.4 | Integration between card and tac server (for indirect download) | Sun 31-05-26 | Thu 04-06-26 | 5 days | 1.6.7.3 | Thales
1.6.7.5 | Integration between TAC and Thales SMDP (for indirect download) | Sun 07-06-26 | Sun 21-06-26 | 10 days | 1.6.7.4 | Thales
1.6.7.6 | Pre-ATP Prod | Mon 22-06-26 | Tue 07-07-26 | 10 days | 1.6.7.5 | Thales
1.6.7.7 | ATP Execution as per ATP Document with CMP PROD | Wed 08-07-26 | Tue 21-07-26 | 10 days | 1.6.7.6 | Airlinq,Batelco,Thales
4.8 | Transfer to support / Project Closure | Wed 22-07-26 | Thu 29-10-26 | 72 days
4.8.1 | OSD-VTP | Wed 22-07-26 | Wed 22-07-26 | 1 day | 1.6.7 | Thales
4.8.2 | OSD-VTP Validation | Thu 23-07-26 | Thu 23-07-26 | 1 day | 4.8.1 | Thales
4.8.3 | OMG writing | Sun 26-07-26 | Wed 29-07-26 | 4 days | 4.8.2 | Thales
4.8.4 | Go-Live | Thu 30-07-26 | Wed 05-08-26 | 5 days | 4.8.3 | Airlinq,Batelco,Thales
4.8.5 | SDVR and handover | Thu 06-08-26 | Wed 12-08-26 | 5 days | 4.8.4 | Thales
1.6.8.6 | FAC | Thu 29-10-26 | Thu 29-10-26 | 1 day | 4.8.4[FS+3 mons]